## Capital - W
APPENDIX A: PROCUREMENT PLAN 1)
AGENCY NAME: Ministry of Agriculture – Hydrometeorological Service
FISCAL YEAR: 2026
EXPENDITURE CATEGORY: Capital
TYPE OF PROCUREMENT: Works
|  |  | Estimated Budget | [5 empty] | Expenditure Phasing
Project Code | Chart of Account Code | Description of Activity |  |  | Procurement Method | Procurement Process (Advertise to Contract Award)5) |  | Contract Duration
2) | 3) |  |  |  | (OT, RT, RFQ, RFP, SS, CP, SH)4) |  |  | (Months)
|  |  | Government | Donor |  | Start | End |  | Q1 | Q2 | Q3 | Q4
2100100 | 7011 | Rollover - Construction of Phase 2 Laboratory at Hydrometeorological Department | 22238500 |  | OT | 23/3/2025 | 2025-12-06 | 7 | 21682537 | 0 | 555963 | 0
2100100 | 7011 | Rollover - Construction of Living Quarter at Wauna, Region #1 | 9675190 |  | RT | 2025-05-11 | 2025-01-12 | 3 | 4800000 | 4633310 | 0 | 241880
Total |  |  | 31913690 | [5 empty] | 26482537 | 4633310 | 555963 | 241880
…………………………. |  | ……………………………… |  |  | ……………………… |  | ……………………………….
Date |  | Programme Manager |  |  | Date |  | Head of Budget Agency
Please type data DIRECTLY onto this form
Notes:
1) Form Header should include Name of the Agency (e.g. Ministry of Finance), Fiscal Year the Plan is being prepared (e.g. 2026), Category of Expenditure (e.g. Current or Capital), Type of Procurement (Goods, Services, Works, Consultancy).
2) Appropriate project code for capital procurement activity.
3) Chart of Accounts code for recurrent procurement activities.
4) The Procurement Methods include Open Tender (OT), Restricted Tender (RT), Request for Quotation (RFQ), Request for Proposal (RFP), Single Source (SS), Community Participation (CP), and Shopping (SH).
5) For the procurement process the start date should be the date the procurement is advertised, or quotation/proposal requested while the end date should be the date the contract is expected to be awarded.

## Capital - G
APPENDIX A: PROCUREMENT PLAN 1)
AGENCY NAME: Ministry of Agriculture – Hydrometeorological Service
FISCAL YEAR: 2026
EXPENDITURE CATEGORY: Capital
TYPE OF PROCUREMENT: Goods
|  |  | Estimated Budget | [5 empty] | Expenditure Phasing
Project Code | Chart of Account Code | Description of Activity |  |  | Procurement Method | Procurement Process (Advertise to Contract Award)5) |  | Contract Duration
2) | 3) |  |  |  | (OT, RT, RFQ, RFP, SS, CP, SH)4) |  |  | (Months)
|  |  | Government | Donor |  | Start | End |  | Q1 | Q2 | Q3 | Q4
2100100 | 7011 | Advanced Commercial Weather Observation System | 19086310 |  | SS | 23/2/2026 | 31/11/2026 |  | 0 | 19086310 | 0 | 0
2100100 | 7011 | Drone with Water Quality Monitoring Sensors | 6000000 |  | SS | 23/2/2026 | 31/11/2026 |  | 0 | 6000000 | 0 | 0
2100100 | 7011 | Automatic Weather Stations (AWS) | 16000000 |  | SS | 23/2/2026 | 31/11/2026 |  | 0 | 16000000 | 0 | 0
Total |  |  | 41086310 | [5 empty] | 0 | 41086310 | 0 | 0
…………………………. |  | ……………………………… |  |  | ……………………… |  | ……………………………….
Date |  | Programme Manager |  |  | Date |  | Head of Budget Agency
Please type data DIRECTLY onto this form
Notes:
1) Form Header should include Name of the Agency (e.g. Ministry of Finance), Fiscal Year the Plan is being prepared (e.g. 2026), Category of Expenditure (e.g. Current or Capital), Type of Procurement (Goods, Services, Works, Consultancy).
2) Appropriate project code for capital procurement activity.
3) Chart of Accounts code for recurrent procurement activities.
4) The Procurement Methods include Open Tender (OT), Restricted Tender (RT), Request for Quotation (RFQ), Request for Proposal (RFP), Single Source (SS), Community Participation (CP), and Shopping (SH).
5) For the procurement process the start date should be the date the procurement is advertised, or quotation/proposal requested while the end date should be the date the contract is expected to be awarded.

## Lineitems (hidden)
0
6211
6221
6222
6223
6224
6231
6241
6242
6243
6251
6252
6253
6254
6255
6261
6262
6263
6264
6265
6271
6272
6273
6281
6282
6283
6284
6291
6292
6293
6294
6301
6302